CONTRACT NO: MUN-BUILD-2025-017 Parties: Between the Local Council of [Redacted City] (the "Council" or "Principal") and BuildRight Contractors Pty Ltd (ABN 12 345 678 901), CRS-registered Grade A contractor (the "Contractor"). Date: July 1, 2025

Project Description: Construction of a 1,200 sqm municipal office extension at 456 Civic Plaza, including structural works, electrical, plumbing, fit-out, and landscaping. Compliance with Building Code [Redacted] required.

Contract Sum: $2,000,000 (fixed lump sum, GST exclusive). Adjustments only via approved variations.

Term / Completion Date: Practical Completion by June 30, 2026. Extension of time claims must be submitted within 7 days of delaying event.

Payment Schedule (Milestones):

- 30% upon contract execution and mobilization ($600,000)

- 20% upon foundation completion ($400,000)

- 20% upon structural frame completion ($400,000)

- 20% upon practical completion ($400,000)

- 10% retention (released 12 months after completion, $200,000)

Variations Any variation (e.g., design changes) must be in writing, approved by Council Project Manager. Valuation: Based on agreed rates or cost-plus 10% margin if rates unavailable. Variation cap: ±15% of original sum without re-tender; exceedance requires new procurement process.

Termination

- For convenience: Council may terminate with 45 days' notice; Contractor paid for work done + reasonable demobilization costs (capped at 5% of sum).

- For default: Council may terminate immediately if Contractor fails to remedy breach within 14 days; Council takes possession of site, materials, and may complete using others—costs deducted from payments.

Defects Liability Period 12 months from Practical Completion. Contractor responsible for rectification at no cost; failure leads to retention withholding.

Insurance & Bonds

- Contractor: Public Liability $20M, Contract Works Insurance full value, Professional Indemnity $5M.

- Performance Bond: 10% of contract sum (bank guarantee, released at completion).

Compliance & Sustainability

- All materials: Minimum 50% locally sourced per CSR policy.

- Environmental: Zero waste to landfill target; weekly reports on recycling.

- Indigenous participation: 5% subcontract value to Indigenous-owned businesses; evidence required.

- Audit & Transparency: All payments, variations, and subcontracts subject to public disclosure under Freedom of Information Act.

Governing Law Laws of [Redacted State]. Disputes via expert determination, then courts in [City].

Entire Agreement & Notices This document constitutes the entire agreement, superseding prior discussions. Notices in writing via email or registered post to addresses specified.

Schedule C – Key Milestones & Specifications (excerpt)

- Week 1–8: Site preparation & foundations (inspections at Week 4 & 8)

- Week 9–20: Structural steel & roofing (safety audit Week 15)

- Week 21–40: Services installation & fit-out (energy efficiency testing Week 35)

- Specifications: Energy rating ≥6 stars, recycled steel where possible, accessible design per standards.

Signatures: [Council Representative] ___________________ Date: __________ [Contractor Representative] ___________________ Date: __________